## Sheet1
Gantt Chart
| Comparing Various Chunking Algorithm | August |  |  |  | September
| in first 2 Months. | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Data Collection and Analysis | bar: August Week 1
Implement Fixed Size Chunking | bar: August Week 2
Implement Recursive Chunking | bar: August Week 3
Implement Document Based Chunking | bar: August Week 4
Implement Semantic Chunking | bar: September Week 1
Implement Agentic Chunking | bar: September Week 2
Compare Metrics | bar: September Week 3 to September Week 4
| Comparing Various Searching Algorithm | August Week 1: October; September Week 1: November
| in last 2 Months. | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Data Collection and Analysis | bar: October Week 1
Implement Semantic Search | bar: October Week 2
Implement Vector Store Flat Index | bar: October Week 3
Implement Hierarchical Indices | bar: October Week 4
Implement Hypothetical Questions and HyDE* | bar: November Week 1
Implement Hybrid Search | bar: November Week 2
Compare Metrics | bar: November Week 3 to November Week 4